## Sheet1
Title of the program	LOC			a_b	b_b	c_b	d_b	Effort	Schedule
findingSponsor.py	125		Organic	2.4	1.05	2.5	0.38	E= a_b x LOC ^ b_b	DEV=c_b x LOC ^ d_b
Feed Forward Backpropagation Neural Network.py	47		Semidetached	3	1.12	2.5	0.35	E= a_b x LOC ^ b_b	DEV=c_b x LOC ^ d_b
Schedule of the project	500		Embedded	3.6	1.2	2.5	0.32	E= a_b x LOC ^ b_b	DEV=c_b x LOC ^ d_b
Designing diagram	109
Designing system view	80					Effort multiplier
	0.861					Cost driver	very low	low	normal	high	very high	extra high
						product complexity (EAF)	0.7	0.85	1	1.15	1.3	1.65
						product complexity (EAF)	very high	1.3
						Intermediate model
							a_b	b_b	c_b	d_b	Effort	Schedule
						Organic	3.2	1.05	2.5	0.38	E= a_b x LOC ^ b_b	DEV=c_b x E ^ d_b
						Semidetached	3	1.12	2.5	0.35	E= a_b x LOC ^ b_b	DEV=c_b x E ^ d_b
						Embedded	2.8	1.2	2.5	0.32	E= a_b x LOC ^ b_b	DEV=c_b x E ^ d_b

COCOMO MODEL
Organic						Organic
	Effort	2.05099475966381	man per month				Effort	3.55505758341727	man per month
	Development time in months	2.36178960186404	months				Development time in months	4.04819786729324	months
	Labor rate	20000					Labor rate	20000

	Productivity	419.796294428919	loc per man per month				Productivity	242.190169862838	loc per man per month
	Average staffing per month	0.868407057955147	full time software personnel				Average staffing per month	0.878182761801191	full time software personnel

	Cost of the project	96880.3619370327					Cost of the project	287831.53054589
Semidetached						Semidetached
	Effort	2.53702521930077	man per month				Effort	3.298132785091	man per month
	Development time in months	2.37241746044826	months				Development time in months	3.79606689027965	months
	Labor rate	15000					Labor rate	15000

	Productivity	339.373843606214	loc per man per month				Productivity	261.05680277401	loc per man per month
	Average staffing per month	1.06938397714431	full time software personnel				Average staffing per month	0.868828943329825	full time software personnel

	Cost of the project	90283.2439180011					Cost of the project	187798.989978447

Embedded						Embedded
	Effort	3.00819706026145	man per month				Effort	3.04162147204214	man per month
	Development time in months	2.38309314352032	months				Development time in months	3.5688941024344	months
	Labor rate	10000					Labor rate	10000

	Productivity	286.217951401484	loc per man per month				Productivity	283.072699188281	loc per man per month
	Average staffing per month	1.26230779877018	full time software personnel				Average staffing per month	0.852258818766127	full time software personnel

	Cost of the project	71688.1378866706					Cost of the project	108552.24933409