## Sheet1
Title of the program	LOC			a_b	b_b	c_b	d_b	Effort	Schedule
findingSponsor.ipynb	94		Organic	2.4	1.05	2.5	0.38	E= a_b x LOC ^ b_b	DEV=c_b x LOC ^ d_b
NeuralNetworkFeedForwardBackpropagation.py	72		Semidetached	3	1.12	2.5	0.35	E= a_b x LOC ^ b_b	DEV=c_b x LOC ^ d_b
Feed_forward_Backpropagation-NeuralNetwork.ipynb	60		Embedded	3.6	1.2	2.5	0.32	E= a_b x LOC ^ b_b	DEV=c_b x LOC ^ d_b
Designing diagram	109
Designing system view	80					Effort multiplier
	0.915					Cost driver	very low	low	normal	high	very high	extra high
Schedule of the project	500					product complexity (EAF)	0.7	0.85	1	1.15	1.3	1.65
						product complexity (EAF)	very high	1.3
						Intermediate model
							a_b	b_b	c_b	d_b	Effort	Schedule
						Organic	3.2	1.05	2.5	0.38	E= a_b x LOC ^ b_b	DEV=c_b x E ^ d_b
						Semidetached	3	1.12	2.5	0.35	E= a_b x LOC ^ b_b	DEV=c_b x E ^ d_b
						Embedded	2.8	1.2	2.5	0.32	E= a_b x LOC ^ b_b	DEV=c_b x E ^ d_b

COCOMO MODEL
Organic						Organic
	Effort	2.18626796145394	person per month				Effort	3.78953113318683	person per month
	Development time in months	2.4170187776113	months				Development time in months	4.14765372058999	months
	Labor rate	20000	USD				Labor rate	20000	USD

	Productivity	418.521432931531	loc per person per month				Productivity	241.454672845114	loc per person per month
	Average staffing per month	0.904530813622636	full time software personnel				Average staffing per month	0.913656584775786	full time software personnel

	Cost of the project	105685.014314483	USD				Cost of the project	314353.258077079	USD
Semidetached						Semidetached
	Effort	2.71589440294144	person per month				Effort	3.53066272382387	person per month
	Development time in months	2.4234685692835	months				Development time in months	3.88767265623533	months
	Labor rate	15000	USD				Labor rate	15000	USD

	Productivity	336.905587716891	loc per person per month				Productivity	259.158144397608	loc per person per month
	Average staffing per month	1.12066417421885	full time software personnel				Average staffing per month	0.908168726130052	full time software personnel

	Cost of the project	98728.2708453236	USD				Cost of the project	205890.913946991	USD

Embedded						Embedded
	Effort	3.23599478945486	person per month				Effort	3.27195028711546	person per month
	Development time in months	2.42993557216358	months				Development time in months	3.65323955744003	months
	Labor rate	10000	USD				Labor rate	10000	USD

	Productivity	282.756944783012	loc per person per month				Productivity	279.649725609572	loc per person per month
	Average staffing per month	1.33172040712733	full time software personnel				Average staffing per month	0.895629819964024	full time software personnel

	Cost of the project	78632.5885023235	USD				Cost of the project	119532.182188675	USD